Five years of strategies to improve hand hygiene in a paediatric cardiovascular intensive care unit. Authors: Andión E.1, Aquino N.1, Herrera C.2, Flores Ortiz C.2, Gallardo R., Moreno G.2, Balestrini M.2 Magliola R.2 1. Department of Epidemiology and Infectious Diseases. 2. Paediatric Cardiovascular Intensive Care Unit.Hospital de Pediatría “Prof. Dr. Juan P. Garrahan”.  Buenos Aires,  Argentina. Introduction: Hand hygiene (HH) is an essential element in the quality and safety of health care. The programme for the implementation of multimodal strategies of the WHO and point prevalence (PP) of compliance of HH was carried out among the personnel of our paediatric cardiovascular intensive care unit (PCICU). In 2008 a prevalence of HH of 18% and in 2009 of 34.4% was observed. Objectives: A prevention programme was implemented to: a) Achieve HH compliance of around 80 %. b) Apply the multimodal strategies of the WHO and the“Five Moments”of the WHO. c) Conduct continuous education programmes for steady and new personnel. Material and Methods: The intervention programmeconsisted of: 1) Planning, development of posters and leaflets for use inside the PCICU; recording of videos for the training of “internal observers”;  2) Selection and training of “observers”; 3) Monitoring of personnel followed by feedback; 4) Classes for steady and new staff members; 5) Use of an “educational box” for the teaching of HH techniques; 6) Monthly report to the personnel of the data found. In 2013 and 2014 the measures were continued and consolidated, accompanied by monitoring, and continuous education for all health-care staff members followed by feedback. On 05/05/2014, World Hand Hygiene Day, asymposium was organized by the Unit for the whole hospital including the hospital management and a tour around the different departments with a giant hand; badges, pocket bottles of alcohol-based handrubs, and hand-shaped candy and cookies were handed out. Results are shown in the following table.

| PERIODS | YEAR | TYPEOF STUDY | Nº OBSERVATIONS | COMPLIANCE % |
| --- | --- | --- | --- | --- |
| PRE INTERVENTION | 2008 | PP | 50 | 18 |
|  | 2009 | PP | 100 | 34,4 |
| INTERVENTIONPROGRAMME | 2010 | WHOMM | 1275 | 86,4 |
|  | 2011 | WHOMM | 1947 | 90,3 |
|  |  | PP | 180 | 52,5 |
|  | 2012 | WHOMM | 486 | 92,8 |
|  |  | PP | 405 | 49,1 |
| POST INTERVENTION | 2013 | PP | 883 | 68,3 |
|  | 2014 | PP | 230 | 62,3 |

WHOMM: WHO Programme of Multimodal strategies. PP: Point prevalenceofcompliance

Conclusion: Ongoing strategy changes are necessary to improve HH, as sustained compliance is difficult over time. Health-care personnel awareness of the need of HH practices may be maintained using different approaches through continuous education.